## Checklist
Product Management Develop Phase Activity Checklist: Product Development and Release Checklist
Activity Group | Activity | Objectives (If Not Applicable Select "Y" for Accomplished) | Accomplished (Y/N)
Develop Phase Product Development Activities | Product Implementation | Define the lead role to manage the end-to-end product development process
| Product Implementation | Identify key stakeholders required in the development phase
| Product Implementation | Complete and coordinate a Develop Phase RACI
| Product Implementation | Add detail to the initial Project Plan completed in the Plan phase
| Product Implementation | Determine appropriate lifecycle for product development
| Product Implementation | Develop required prototypes and mock-ups (As applicable)
| Product Implementation | Plan hand off to manufacturing and operations
| Product Implementation | Design physical packaging
| Product Implementation | Address issues (As applicable)
| Product Requirements Refinement | Review "good enough scenario." Update Product Requirements Document (PRD)
| Product Requirements Refinement | Review PRD for missing requirements or lack of detail
| Product Requirements Refinement | Review PRD and clarify vague requirements
| Product Requirements Refinement | Identify and remedy implementation limitations
| Product Verification Activities | Update product test strategy
| Product Verification Activities | Define minimum test acceptance levels
| Product Verification Activities | Define compliance requirements
| Product Verification Activities | Release product to supporting operational function
| Release and Configuration Management | Identify version control process
| Release and Configuration Management | Develop formal change management process
| Release and Configuration Management | Verify development and testing configurations and environments
| Release and Configuration Management | Manage overall product build process
| Release and Configuration Management | Validate final components to include packaging for distribution or operations
| Release and Configuration Management | Ensure all required process steps are completed
| Release and Configuration Management | Track defects, issues, and develop remediation plan
| Release and Configuration Management | Complete product release checklist--release product

## Issues Log
Current Product Development Issues
Issue | Proposed Action